## project
P&O: CompSci
[9 empty] | Periodetrend: |  | 13 |  |  |  | Plan |  |  | Reality |  | % Completed |  | Werkelijk (meer dan gepland) | % Voltooid (meer dan gepland)
|  | PLAN | PLAN | WERKELIJK | WERKELIJK | PROCENT | VERANTWOOR- | TEAM | PERIODE
| ACTIVITEIT | BEGIN | DUUR | BEGIN | DUUR | VOLTOOID | DELIJKE(N) | MEMBERS | 2016-02-09 | 2016-02-16 | 2016-02-23 | 2016-03-01 | 2016-03-08 | 2016-03-15 | 2016-03-22 | 2016-04-12 | 2016-04-19 | 2016-04-26 | 2016-05-03 | 2016-05-10 | 2016-05-17
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
ADMINISTRATIE | Orienteering | 1 | 1 | 1 | 1 | 100% | Arno (CEO) | Everyone
| Administration | 1 | 13 | 1 | 13 | 100% | Arne (CAO) | Everyone
| Intermediate report | 2 | 4 | 2 | 4 | 100% | Arne (CAO) | Everyone
| Final report | 7 | 5 | 9 | 4 | 100% | Arne (CAO) | Everyone
HARDWARE | Robot Adjustments | 2 | 1 | 2 | 1 | 100% | Frederik | Frederik, Kristof, Arno
| Finetuning | 2 | 11 | 2 | 12 | 95% | Pieter | Everyone
SOFTWARE | Assignment 1st semester | 2 | 5 | 2 | 11 | 90% | Pieter | Pieter, Wouter, Arno
| Manual Intervention | 2 | 1 | 2 | 1 | 100% | Pieter | Pieter, Frederik, Arno
| Packet Server | 4 | 2 | 4 | 9 | 100% | Pieter | Pieter, Wouter
| Weighted Graph | 3 | 3 | 4 | 7 | 100% | Arne (CAO) | Arne, Frederik, Wouter
| Shortest path | 4 | 3 | 4 | 5 | 100% | Wouter | Wouter, Pieter, Kristof
| Obstacle detection | 7 | 2 | 7 | 3 | 100% | Pieter | Frederik, Pieter, Kristof
| GUI on all devices | 9 | 3 | 6 | 6 | 90% | Arne (CAO) | Arne, Frederik, Kristof
| Spookserver | 4 | 6 | 5 | 5 | 100% | Wouter | Wouter, Pieter, Kristof
| RESTServer | 4 | 2 | 3 | 2 | 100% | Pieter | Pieter
| Optimizing detection algorithms | 5 | 6 | 6 | 6 | 100% | Arno (CEO) | Everyone
| Day | [7 empty] | 2016-02-16: 2016-02-17; 2016-03-01: 2016-03-01; 2016-03-08: 2016-03-08; 2016-05-10: 2016-05-10; 2016-05-17: 2016-05-17
| Deadline | [7 empty] | 2016-02-16: Plan tussentijdse; 2016-03-01: Tussentijdsverslag; 2016-05-10: Eindverslag; 2016-05-17: Finale
[10 empty] | demo |  |  | Tussentijdse | [7 empty] | demo
demo
| Length | [7 empty] | 2016-03-01: 10p.; 2016-05-10: 20p