## project
P&O: CompSci
[9 empty] | Periodetrend: |  | 6 |  |  |  | Plan |  |  | Reality |  | % Completed | Werkelijk (meer dan gepland) | % Voltooid (meer dan gepland)
|  | PLAN | PLAN | WERKELIJK | WERKELIJK | PROCENT | VERANTWOOR- | TEAM | PERIODE
| ACTIVITEIT | BEGIN | DUUR | BEGIN | DUUR | VOLTOOID | DELIJKE(N) | MEMBERS | 2015-09-28 | 2015-10-05 | 2015-10-12 | 2015-10-19 | 2015-10-26 | 2015-11-02 | 2015-11-09 | 2015-11-16 | 2015-11-23 | 2015-11-30 | 2015-12-07 | 2015-12-14
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
ADMINISTRATIE | Orienteering | 1 | 2 | 1 | 1 | 100% | Arno (CEO) | Everyone
| Administration | 1 | 12 | 1 |  | 50% | Arne (CAO) | Everyone
| Brainstorm | 2 | 1 | 1 | 2 | 100% | Arno (CEO) | Everyone
| Verslag 1 (planning) | 1 | 2 | 1 | 2 | 100% | Arne (CAO) | Everyone
| Verslag 2 (hard-/software) | 2 | 2 | 3 | 1 | 100% | Arne (CAO) | Everyone
| Verslag 3 (experiment) | 3 | 2 | 4 | 1 | 100% | Arne (CAO) | Everyone
| Intermediate report | 2 | 4 | 4 | 2 | 10% | Arne (CAO) | Everyone
| Final report | 7 | 4 | 4 |  | 0% | Arne (CAO) | Everyone
HARDWARE | Building of Robot | 2 | 2 | 2 | 2 | 100% | Frederik | Frederik, Kristof, Arno
| Control Engine | 2 | 2 | 2 | 2 | 100% | Pieter | Pieter, Wouter, Arne
| Steering Vehicle | 3 | 2 | 4 | 2 | 95% | Frederik | Frederik, Arne, Kristof
| Sensor Rotation | 3 | 3 | 6 |  | 0% | Kristof | Kristof, Arno
| Perform experiments | 4 | 6 | 4 |  | 50% | Kristof | Everyone
| Finetuning | 5 | 1 | 5 |  | 50% | Arno (CEO) | Everyone
SOFTWARE | Manual Driving | 2 | 3 | 2 |  | 50% | Pieter | Pieter, Wouter, Arne
| Connection PC/BrickPi | 2 | 1 | 2 | 1 | 100% | Wouter | Pieter, Wouter, Arne
| Interface HTML5 | 3 | 2 | 2 | 3 | 0% | Arne (CAO) | Arne, Wouter, Pieter
| Commando Driving | 3 | 3 | 4 |  | 0% | Arno (CEO) | Arno, Kristof, Frederik
| Camera Data Conversion | 4 | 2 | 3 |  | 0% | Kristof | Kristof, Frederik, Pieter
| Camera Recognition | 4 | 6 | 3 |  | 0% | Frederik | Arne, Frederik, Arno
| Camera Finetuning | 9 | 3 |  |  | 0% | Arne (CAO) | Arne, Frederik, Kristof
| Following White Line | 5 | 6 |  |  | 0% | Frederik | Frederik, Pieter, Wouter
| Advanced HTML5 Interface | 5 | 3 |  |  | 0% | Wouter | Arno, Arne, Wouter
| Day | [7 empty] | 2015-10-05: 2015-10-06; 2015-10-12: 2015-10-13; 2015-10-19: 2015-10-20; 2015-11-02: 2015-11-04; 2015-11-09: 2015-11-09; 2015-12-07: 2015-12-09; 2015-12-14: 2015-12-14
| Deadline | [7 empty] | 2015-10-05: Planning; 2015-10-12: Hard- en; 2015-10-19: Experiment; 2015-11-02: Tussentijds; 2015-11-09: Tussentijdse; 2015-12-07: Finaal; 2015-12-14: Finale demo
[10 empty] | Ontwerp | software |  |  | verslag | Demonstratie |  |  |  | verslag | Presentatie
Oplossingsuggestie
| Length | [7 empty] | 2015-10-05: 1 pag.; 2015-10-12: 2 pag.; 2015-10-19: 2 pag.